## Township Maintenancwe23.09.2025
Township Maintenance Department - Daily Report Date : 23/09/2025
Sl. No. | Details
|  | Actual |  | Present | OFF / Leave / Absent | Approve GT
1 | Total no. of On Roll Employees | 14 |  | 11 | 3 | 11
2 | Total no. of On Associate Employees | 51 |  | 41 | 10 | 87
3 | MBC | As per PO |  | Present | OFF / Leave / Absent
(i) | M/s. Kanha Enterprises | 11 |  | 11 | 0
(ii) | Maa Sarala | 17 |  | 15 | 2
| Total no. of On Roll and out Sourced Employees | 93 |  | 78 | 15 | 98
4 | JBN
(i) | Samaleswari Construction | 15 |  | 13 | 2
5 | AMC
(i) | Global Elevator (Phase - II) | 2 |  | 2 | 0
6 | JBC | PO No. | Work Description | PO (Qty) | Previous Cumulative Qty. | Today Achieved Qty.
(i) | Pappi Devi | 4500205759 | Interior Wall Paint | 5000 M2 | 4766.73
|  |  | Exterior Wall Paint | 500 M2 | 135.84
|  |  | Wall Putty | 500 M2 | 95.49
(ii) | Manoj Enterprises | 4500205760 | Interior Wall Paint | 5000 M2 | 5089.73
|  |  | Exterior Wall Paint | 500 M2 | 405.85
|  |  | Wall Putty | 500 M2 | 95.23
(iii) | Real Waterproofing System | 4500203332 | Pu Pressure Grouting And 0-10 Points At single Place | 1000 EA | 179
|  |  | Cementitious Waterproofing | 200 M2 | 274.195
|  |  | Epoxy In Tile Joint Filling | 800 M2 | 650.06
|  |  | Dismantling Work Of Brick Bat Coba Or Screed Concrete Or Tiles Flooring | 300 M2 | 193.605
|  |  | Non Shrink Grouting | 50 EA | 23
|  |  | Pu Pressure Grouting And 10-20 Points At Single Place | 1000 EA | 475
|  |  | Pu Pressure Grouting And 10-20 Points At Single Place | 1000 EA | 427
|  |  | Dr. Fixit Roof seal Classic Waterproofing Coating | 150 M2 | 15.94
7 | Total Maintenance Job (My Gate Complain) | Job No | Complain Received from details | Complain Completed Details | Pending Details | Feedback
(i) | Civil Work | 5064 | Entrance grill painting work start at M3 building ground floor |  | work in progress
|  | 5317 | Vehicle parking painting near L & M block |  | Work stopped for certain time due to rain
|  |  | N & O Block parking painting |  | Work stopped for certain time due to rain
|  |  | E3-701 Putty & painting work |  | Work in progress
|  |  | NEW GET D-914 Putty & painting work |  | Work in progress
|  |  | A & C Block no parking painting |  | Work in progress
|  |  | D-001 Putty & painting |  | Work in progress
|  |  | E3-603 Kitchen sink repairing |  | Work in progress
|  |  | C-203(Vacant room) Both bathroom wall tiles fixing |  | Work in progress
|  |  | NEW GET CF-102(Vacant room) Full flat painting |  | Work in progress
|  |  | H-604 Putty & painting |  | Work in progress
|  |  | M3-604(Vacant room) Full flat painting |  | Work in progress
|  |  | Temple lord Vishwakarma stage marble work |  | Work in progress
| Total = | 13 | 13 |  | 13
(ii) | Plumbing Work |  | FU1-005 Kitchen sink waste coupling damage | New installed |  | Outstanding
|  |  | E3-601 Kitchen sink cock damage | New installed |  | Outstanding
| Total = | 2 | 2 | 2
(iii) | Seepage Work | 5888 | E2-701 Balcony ceiling seepage |  | Work will start as soon as possible
|  | 6769 | E2-804 Hall ceiling seepage |  | Work will start as soon as possible
|  |  | J-302 Master bedroom ceiling seepage |  | Work will start as soon as possible
|  | 8893 | IB Basement floor seepage |  | Work under progress
|  | 9203 | O-601 Bedroom wall seepage |  | Work will start as soon as possible
|  | 9235 | M1-803 Toilet window site seepage |  | Work in progress
|  | 9321 | G-603(Vacant room) Bedroom wall seepage |  | Work in progress
|  | 9426 | M1-604 Hall wall seepage |  | Work will start as soon as possible
|  | 9647 | EH3-72 Kitchen & balcony ceiling seepage |  | Work will start as soon as possible
|  | 9664 | E2-008 Balcony ceiling seepage |  | Work in progress
|  | 9699 | J-202 Bedroom wall seepage |  | Work will start as soon as possible
|  | 9762 | FU1-004 Balcony shaft wall seepage |  | Work in progress
|  | 9751 | FU7-104Bathroom ceiling seepage |  | Work in progress
|  | 9781 | E3-302 Bedroom hall wall seepage |  | Work will start as soon as possible
|  | 9850 | J-702 Bedroom wall seepage |  | Work will start as soon as possible
|  | 9936 | K-502 Hall wall seepage |  | Work will start as soon as possible
|  | 9996 | M2-001 Hall wall seepage |  | Work in progress
|  | 10070 | E1-607 Bedroom ceiling seepage |  | Work in progress
|  | 10145 | NEW GET A-234 Bathroom ceiling seepage |  | Work will start as soon as possible
|  | 10127 | O-704 Bedroom ceiling seepage |  | Work will start as soon as possible
|  | 10154 | E3-704 Bedroom wall seepage |  | Work will start as soon as possible
|  | 10169 | M2-405 Bathroom ceiling seepage |  | Work will start as soon as possible
|  | 10179 | NEDW GET A-406 Bedroom ceiling seepage |  | Work will start as soon as possible
|  | 10180 | NEW GET A-432 Bedroom ceiling seepage |  | Work will start as soon as possible
|  | 10279 | NEW GET DF-601 Bedroom ceiling seepage |  | Work will start as soon as possible
|  | 10318 | NEW GET DF-801 Bathroom ceiling seepage |  | Work will start as soon as possible
| Total = | 26 | 26 |  | 26
(iv) | Carpentry Work | 10305 | M1-205-Door jam | Balcony door repair |  | Very Good
|  | 10303 | FU7-503-Main door lock issue | Main door repair |  | Very Good
|  | 10280 | FU5-004-Almirah door hinges loose | Almirah door hinges repair |  | Very Good
|  | 10283 | M3-202-Kitchen drawer issue | Kitchen drawer repair |  | Very Good
|  | 9698 | M1-501-Hanger & photo frame need to be fixed | Hange & photo frame fixed |  | Very Good
|  | 10289 | J-604-Bed Room door jam | Door repair |  | Very Good
|  | 10287 | E1-508-Door lock issue | Door lock repair |  | Very Good
|  | 10291 | FU7-602-Wire nesh need to be fixed at balcony | Wire mesh fixed |  | Very Good
|  | 10294 | CF-305-Kitchen door hinges loose | Kitchen door hinges repair |  | Out Standing
|  | 10265 | DF-501-Cupboard lock not working | New Lock installed |  | Very Good
|  |  | FU6-604-Utensil stand fixed | Utensil stand fixed |  | Very Good
|  | 10375 | New Get D-1114-Almirah lock issue | New Almirah lock installed |  | Very Good
| Total = | 12 | 12 | 12
(v) | Electrical Work |  | New get-D-508 | Bed room supply problem |  | very Good
|  |  | New get-D-418 | Fan regulator,6A switch, change |  | very Good
|  |  | Central ground | Light fitting
| Total = | 3 | 3 | 3
8 | Any Other Activity | Carpentry
Temple curtain stitching work under progress.
C-203-Maintenance work under progress (Vacant room)
M3-501-Maintenance work under progress (Vacant room)
L-001-Sofa work under progress(Vacant Room)
E-206--Maintenance work under progress (Vacant room)
New Get 11th floor 13 nos room Almirah completed & 01 nos under progress
Civil
Shifting of light poles and associated works at Central Ground.